Blog: Learnings from setting up large-scale adaptive management programs

Authors: Jane Lonsdale, Duncan Green and Mark Pruden

What is adaptive management and will it make a difference?

Adaptive management (AM) can be distinguished from more traditional aid approaches by its ability to detect and respond both to programs’ own ‘learning by doing’ and to windows of opportunity or threat, e.g. a new leader; a crisis that shakes the status quo and makes decision makers suddenly become open to new ideas; or a new social movement or other organization that offers new possibilities of change. The level of analysis and decision-making required to remain relevant and incorporate learning is markedly higher than in traditional aid programs.

Adaptive management’s promise/hypothesis is that adaptive programs will yield better results, because they ‘dance with the system’, enabling aid dollars and relationships to be brought to bear with greater effectiveness in a complex and uncertain world of shifting political players, social norms and social organization.

So far, however, many of the best-known examples of the explicit use of AM have been in relatively small programs. DT Global’s Tracking Adaptive Management Initiative (TAMI) aims to fill that gap by working with larger-scale DFAT programs trying to apply AM. Aiming to better understand the distinct challenges or advantages they face, and make recommendations to DFAT, DT Global and the wider development community about how this learning can lead to improved practice. The three programs are:

Building Community Engagement in Papua New Guinea (BCEP) – a largely civil society focused program in Papua New Guinea.

Partnership for Inclusive Prosperity (PROSIVU) – an economic governance program in Timor Leste.

Tautai – an economic governance program in Samoa.

This blog summarises key findings from Phase 1 of TAMI, where we compared the enabling/constraining conditions for adaptive management across the three programs at inception, and what was learnt from applying an ‘intentional approach’ to AM from program commencement. All three programs baselined their adaptive conditions, using DT Global’s AM framework, then agreed a level of ambition - how adaptive should they and could they be, and a strategy for achieving this adaptive ambition. This common approach allows some level of analysis across the programs, despite differences in political contexts, program histories and budgets.

What did the baselines tell us?

All three programs faced mixed initial conditions for adaptive management, with several significant factors at times frustrating efforts to be adaptive. In summary:

- BCEP had the advantage of a good design: existing components and partners across a wide range of actors that should collectively be able to influence change. However, a heavily pre-allocated budget, greatly limited the flexibility needed to respond to emerging opportunities.

- PROSIVU had the advantage of some good existing relationships, staff and activities, but faced the challenge of transitioning from being a technical assistance program to a more politically informed program, coupled with minimal budget flexibility.

- Tautai had the advantage of high flexibility but faced challenges in creating relationships with a new government and therefore identifying entry points with real transformative potential. Some of the above factors were within DFAT control e.g. budget size and flexibility, while some were within DT Global control, e.g. getting the right staffing and MEL systems in place. Context-related factors were more often outside the control of the program.

Yet positively, all three programs had teams were willing to question assumptions, recognising that solutions to their chosen issues were not known at the start. This lack of rigidity is far from the norm in development.

Our insights on the enabling/constraining inception phase conditions for AM at scale:

Adaptive spectrum and nuance: adaptive or non-adaptive doesn’t need to be a dichotomy, at least for large-scale programming. It can be seen as a spectrum and one that can be used in a nuanced way that encouraged different levels of and approaches to adaptiveness within one large scale program.

Requires high degree of thinking: to continuously understand context, question approaches and solutions, and make decisions across program strategy, delivery, MEL, operations and relationships with stakeholders.

Resourcing intensity: Setting up for AM at large scale highlighted its resource intensiveness and this should be factored into design and procurement.

Locally led – AM connection: The process of developing adaptive baselines and strategies further underlined a strong interconnection between adaptive management and locally led development. National staff are best placed on understanding the politics and realistic implementation expectations.

Role of DFAT in responding to context changes: The programs require sufficient flexibility within contract and program management structures, as well as space and trust to manage the programs; managing the programs is what DFAT are contracting out. However, the programs will likely need to earn this trust.

Role of DFAT in political economy analysis: DFAT can play a useful role bringing broader political economy insights to inform adaptive programming, while drawing on program analysis to inform its own diplomatic responsibilities.

- Value for money for AM: Maintaining a focus on VfM, explaining how AM can support effectiveness and efficiency, can help a program justify its approach.

- Intentionality advantages: Some initial wins emerged even during the inception process. These included: better dialogue with DFAT, leading to enhanced understanding of the inherent uncertainties involved in programming in complex contexts, and flexibility on issues such as setting up ‘responsive funds’ to seize windows of opportunity or support new development actors.

So what should we do differently going into large scale adaptive programs?

| For clients/ donors | For implementers |
| --- | --- |
| From design onwards consider AM as a spectrum that can be applied to differing degrees depending on the need, and applied with nuance within the same program. | Ensure leadership teams include some staff that already understand adaptive management, ideally national staff and invest in building leadership in capacity in AM where required. |
| Include a decent percentage of unallocated budget (through a ringfenced flexible funding mechanism or similar). | Build the team around several top national staff with a deep understanding of the local political operating context and the necessary networks. |
| Invest in training and support for staff to understand what is different about managing adaptive programs. | Invest in briefing the client/donor upfront and repeatedly on adaptive management in practice. |
| Ensure work to be inherited from predecessor programs is considered in the design and procurement phases including what flexibility and culture shifts a move to AM will require. | Invest in shifts in culture between programs, particularly new phase programs that move from non-AM to AM programs. |

What’s next for TAMI?

We plan to report back next year on the first period of implementation (Phase 2) as well as the ‘proof of the pudding’ of effectiveness: has working adaptively made a difference in the results achieved?

Up for an exchange on this? We’d be really interested to hear others’ experiences of working adaptively at scale.

About the authors:

Jane Lonsdale is DT Global’s Adaptive Management Lead and Technical Director for BCEP. She has designed and led adaptive governance and civil society programs in multiple regions, including programs in Tanzania, Myanmar and Papua New Guinea.

Dr Duncan Green is Professor in Practice in International Development at the London School of economics, and author of How Change Happens and From Poverty to Power: How Active Citizens and Effective States can Change the World. He is a critical friend on the DT Global-managed BCEP program.

Mark Pruden is Knowledge Lead for DT Global. He has previously been DT Global’s Country Director in both Myanmar and Indonesia and has held leadership roles on DFAT-funded programs across Asia and the Pacific.